## Tabelle1
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions.
Enter Company Name in cell B2. | TGÖ_Website
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Eddy |  | Project Start | 2021-10-29
| Vera | Werner
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Eddy & Vera | Externe | Project Week | 1 | [7 empty] | 2021-10-29 | [6 empty] | 2021-11-05 | [6 empty] | 2021-11-12 | [6 empty] | 2021-11-19 | [6 empty] | 2021-11-26 | [6 empty] | 2021-12-03 | [6 empty] | 2021-12-10 | [6 empty] | 2021-12-17 | [6 empty] | 2021-12-24 | [6 empty] | 2021-12-31 | [6 empty] | 2022-01-07 | [6 empty] | 2022-01-14 | [6 empty] | 2022-01-21 | [6 empty] | 2022-01-28 | [6 empty] | 2022-02-04 | [6 empty] | 2022-02-11 | [6 empty] | 2022-02-18 | [6 empty] | 2022-02-25 | [6 empty] | 2022-03-04 | [6 empty] | 2022-03-11 | [6 empty] | 2022-03-18 | [6 empty] | 2022-03-25 | [6 empty] | 2022-04-01 | [6 empty] | 2022-04-08 | [6 empty] | 2022-04-15 | [6 empty] | 2022-04-22 | [6 empty] | 2022-04-29 | [6 empty] | 2022-05-06 | [6 empty] | 2022-05-13 | [6 empty] | 2022-05-20 | [6 empty] | 2022-05-27 | [6 empty] | 2022-06-03 | [6 empty] | 2022-06-10 | [6 empty] | 2022-06-17 | [6 empty] | 2022-06-24 | [6 empty] | 2022-07-01 | [6 empty] | 2022-07-08 | [6 empty] | 2022-07-15 | [6 empty] | 2022-07-22 | [6 empty] | 2022-07-29 | [6 empty] | 2022-08-05 | [6 empty] | 2022-08-12 | [6 empty] | 2022-08-19 | [6 empty] | 2022-08-26 | [6 empty] | 2022-09-02 | [6 empty] | 2022-09-09 | [6 empty] | 2022-09-16 | [6 empty] | 2022-09-23 | [6 empty] | 2022-09-30 | [6 empty] | 2022-10-07 | [6 empty] | 2022-10-14 | [6 empty] | 2022-10-21 | [6 empty] | 2022-10-28 | [6 empty] | 2022-11-04 | [6 empty] | 2022-11-11 | [6 empty] | 2022-11-18 | [6 empty] | 2022-11-25 | [6 empty] | 2022-12-02 | [6 empty] | 2022-12-09 | [6 empty] | 2022-12-16 | [6 empty] | 2022-12-23 | [6 empty] | 2022-12-30 | [6 empty] | 2023-01-06 | [6 empty] | 2023-01-13 | [6 empty] | 2023-01-20 | [6 empty] | 2023-01-27 | [6 empty] | 2023-02-03 | [6 empty] | 2023-02-10 | [6 empty] | 2023-02-17 | [6 empty] | 2023-02-24 | [6 empty] | 2023-03-03 | [6 empty] | 2023-03-10 | [6 empty] | 2023-03-17 | [6 empty] | 2023-03-24 | [6 empty] | 2023-03-31 | [6 empty] | 2023-04-07 | [6 empty] | 2023-04-14 | [6 empty] | 2023-04-21 | [6 empty] | 2023-04-28 | [6 empty] | 2023-05-05 | [6 empty] | 2023-05-12 | [6 empty] | 2023-05-19 | [6 empty] | 2023-05-26 | [6 empty] | 2023-06-02 | [6 empty] | 2023-06-09 | [6 empty] | 2023-06-16
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-10-29 to 2023-06-21
| Aufgaben | zugewiesen zu | Progress | Soll Dauer | Ist Dauer | SOLL START | IST ENDE | IST START | IST ENDE | Progress | Restdauer | bar: 2021-10-29 to 2023-06-21
Protokolle bei Meetings
| PROJEKTMANAGEMENT | Eddy, Vera
Planung&Strategie
| Kick -Off | Eddy, Vera, Werner, Marius |  |  |  | Fr.29.10.2021 |  | Fr.29.10.2021
| Technische Anforderungen - Meeting | Eddy, Vera / Werner/ / Thorsten Wendel
| Bestandsaufnahme | Eddy, Vera
Beginn
| Projektplanung | Eddy, Vera
Umsetzung
| Konzept (Mobile) | Vera
| Konzept Feedback | Eddy, Vera/Werner
| Design (Mobile) | Vera
| lizenzen/Rechte prüfen | Eddy, Vera
| Design Feedback | Eddy, Vera / Werner
| Übergabe | Eddy, Vera
| Entwicklung (Mobile) | Eddy
Schritt 1
Schritt2
| Prototypen | Eddy, Vera
| Mehrere Schleifen | Eddy, Vera
| Prüfen | Eddy, Vera
| Design | Vera
| lizenzen/Rechte prüfen | Eddy, Vera
| Design Feedback | Eddy, Vera / Werner
| Übergabe | Eddy, Vera
| Entwicklung (Mobile) | Eddy
Schritt 1
Schritt2
| Prototypen | Eddy, Vera
| Mehrere Schleifen | Eddy, Vera
| Prüfen | Eddy, Vera
Vollendung
| Launch | Eddy, Vera
| Aufbereitung Projekt | Eddy, Vera
Nach dem Launch
| Wartung und Instandhaltung | Eddy, Vera / Abteilungsleiter
| Konzept | Eddy, Vera
Inhalte verstehen
Inhaltliche Analyse
Ziele
Zielgruppe analysieren
Inhalte konzipieren
2-3 Tonalitäten
Storyboard & Strukturen
| Design | Vera
Seite konzipieren
Visuelle Analyse
Designkonzept
Seite gestalten
Umsetzung
Rechte
Quality-Check
| Entwicklung | Eddy
Beispiel
| Task 1 |  |  | 2021-10-29 | 2021-11-02 |  |  |  |  | 50%
| Task 2 |  |  | 2021-10-31 | 2021-11-05 |  |  |  |  | 50%
| Task 3 |  |  | 2021-11-05 | 2021-11-08
| Task 4 |  |  | 2021-11-05 | 2021-11-07
| Task 5 |  |  | 2021-11-05 | 2021-11-08